## Sheet1
PROJECT TITLE |  | OK! Food Delivery
TEAM |  | 1 - DE
NO | TASK | PIC | STATUS | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4
|  |  |  | 29 | 30 | 31 | 1 | 2 | 5 | 6 | 7 | 8 | 9 | 12 | 13 | 14 | 15 | 16 | 19 | 20 | 21 | 22 | 23
1 | Project Initiation Document | Syaikh | Done | bar: WEEK 2 5 to WEEK 2 6
2 | Gantt Chart | Ridho | Done | bar: WEEK 2 5
3 | Part 1: Entity Relationship Diagram | All | Done | bar: WEEK 1 31 to WEEK 1 2
4 | Part 2: SQL and Database | Fadhli | Done | bar: WEEK 2 5 to WEEK 2 6
5 | Part 3: Exploratory Data Analysis | Syaikh | Done | bar: WEEK 2 6 to WEEK 2 7
6 | Part 4: ETL dan Scheduled Job | Ridho | Done | bar: WEEK 2 7 to WEEK 2 8
7 | Part 5: Revenue & Customer Monitoring | Syaikh | Done | bar: WEEK 2 9 to WEEK 3 15
8 | User Manual | All | Done | bar: WEEK 3 14 to WEEK 3 16
9 | User Testing | All | Done | bar: WEEK 3 14 to WEEK 3 16
10 | Final Presentation | All | Done | bar: WEEK 4 19